## Project
project_code | project_name | description | budget_allocated | start_date | end_date
PROJ-TITAN-001 | Titanium Chassis Assembly Line v2 | Redesign of the primary structural chassis for the X-500 platform. Mil-Spec compliance required. | 2500000 | 2026-04-01 | 2026-12-31

## Resources
resource_code | resource_name | resource_type | standard_cost_rate
ENG-SR-001 | Lead Structural Engineer | ENGINEER | 95
ENG-SR-002 | Senior FEA Analyst | ENGINEER | 88
ENG-JR-003 | Junior Test Engineer | ENGINEER | 55
MCH-CNC-001 | 5-Axis CNC Mill (Haas UMC-750) | MACHINE | 150
VND-TI-001 | VSMPO-AVISMA (Titanium Supplier) | VENDOR | 0

## Tasks
project_code | task_code | task_name | planned_duration_hours | planned_cost | dependency_task_code
PROJ-TITAN-001 | WBS-1.0 | Requirements Freeze & Kick-Off | 80 | 15000
PROJ-TITAN-001 | WBS-2.0 | Preliminary Design Review (PDR) | 320 | 65000 | WBS-1.0
PROJ-TITAN-001 | WBS-3.0 | Critical Design Review (CDR) | 480 | 120000 | WBS-2.0
PROJ-TITAN-001 | WBS-4.0 | FEA Simulation & Fatigue Analysis | 600 | 180000 | WBS-3.0
PROJ-TITAN-001 | WBS-5.0 | Titanium Billet Procurement | 200 | 750000 | WBS-3.0
PROJ-TITAN-001 | WBS-6.0 | CNC Machining (Prototype) | 400 | 350000 | WBS-5.0
PROJ-TITAN-001 | WBS-7.0 | NDT Inspection & Quality Gate | 160 | 95000 | WBS-6.0
PROJ-TITAN-001 | WBS-8.0 | Environmental Stress Screening (ESS) | 240 | 130000 | WBS-7.0
PROJ-TITAN-001 | WBS-9.0 | Mil-Spec Certification Package | 320 | 200000 | WBS-8.0
PROJ-TITAN-001 | WBS-10.0 | Production Readiness Review (PRR) | 120 | 85000 | WBS-9.0